HKUST iGem2009

Minutes of the 12th General Meeting

Date:	25/6/2009

Time:	17:35 -18:55

Place:	Room 5509

Attending:   Alex(Wong Chun Hung), Angela(Liu Yang), Bonnie(Lam Ki Yan), , Elaine(CAI Yilei), Helen(Zhong Wanting), Joyce(Zhang Junyi), Kelvin(Min Kai Kei), Luo Yunqiu, Lavinia(Li Yunzi), Sandy(Wong Pui Shan), Swift(Chen Xihan),Vito(Ng Wang Ki), Zhou Chaoxu, Tony(Ho Wai Pang)

Absent:	Aileen(Pan Huilin), Emma(Chen Xinru), Jessica(Zhang Chuchu), Philip(Yang Yang), Richard(Tian Guangman), Prof. King Chow

Host:	Lavinia

Recorder:	Vito

Report on progress

- Adopt the agenda for the 12th regular meeting and the minutes for the 11th regular meeting.

Discussion items

  - Progress of each group by group representatives

    - Receptor

- Kelvin posted the whole sequence of the receptor on iGEM2009 forum.

- Odr-10 mid-part to replace the I7 receptor’s mid-part, primers for PCR designed.

- Jessica Tang helped Kelvin for designing the whole sequence and primers.

- KC replied Kelvin on forum, but Kelvin cannot interpret the message because Kelvin has not talked to Chuchu yet about the message.

- Kelvin also mentioned about KC’s message and expressed his opinion about other groups also, and reminded others to chase up with the whole team. And also reminded all members to appoint and plan the lab training or lab works in advance.

    - Signaling

- KC suggests buying ARO9-delta strain directly and crosses it with WIF-alpha.

- Emma and Vito suggest that do the gene disruption themselves directly on the WIF-alpha strain.

- Group 2 will focus on two directions; one is to determine the feasibility of genetic crossing, and the detailed protocol, materials for gene disruption.

    - Attractant and toxin

Attractant part:

- Every experiment data, protocols recorded in logbook during lab training.

- Swift mentioned they have not figure out which plasmid to use, but they have figured out the way how to integrate the ARO9 gene inside the primer, but they have to use the fus-1 gene for promotion of whole sequence.

Toxin part:

- Sequence of BT toxin is still under searching, but Lavinia had figured there are some listed on the book she has borrowed from library.

- Concentration of BT toxin under searching within literature.

  - Other important things:

- Kelvin mentioned the change the amino acid can enhance the accuracy of localization of protein, but he didn’t know about what the exact method is.

- Swift mentioned that every members need to find out the protocol and materials needed by themselves in advance.

- Swift mentioned all members should tell Jessica all lab works in advance, Vito suggested that all lab training should be told to Jessica the day before and not after 4:00pm.

- Kelvin mentioned that all the members need to learn and optimize techniques ASAP, hence it is almost the end of June.

- Tony mentioned the planning of schedule is very important because we have to work in to yeast’s schedule, but not force yeast to work in our schedule. Kelvin also mentioned all members can prepare stocks so we can have something to do inside the lab if experiment failed.

- Kelvin mentioned the planning of experiment should include control.

- Kelvin suggested that we have to plan the integration of all parts in advance.

- Tony reminded Group 4 to revise their milestone plan and resend it back to Tony, since the milestone plan is too tight that seems unrealistic.

- Joyce asked about the matter of Visa, Tony said that the matter should not be done too early, and will be handled after return of KC.

  - Discussion on person-in-change for the next meeting

    - Joyce will be the PIC for the next meeting.

Meeting adjournment and next meeting

The meeting was adjourned at 18:55.